## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
P.I.S.T.A
Base de Dados |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Fernando,Miguel,Pedro,Rafael,Sara
Project start date: | 2024-03-05 |  |  |  |  | março | [27 empty] | abril | [34 empty] | maio
Scrolling increment: | -1 | time axis 2024-03-04 to 2024-05-28
TASK | Category | Assigned to | Progress | Start | Days | time axis 2024-03-04 to 2024-05-28
Definição de Sistema
Contextualização | High Risk |  | 100% | 2024-03-05 | 2
Fundamentação | High Risk |  | 100% | 2024-03-05 | 2
Objetivos | High Risk |  | 100% | 2024-03-05 | 2
Viabilidade | High Risk |  | 100% | 2024-03-05 | 2
Recursos | High Risk |  | 100% | 2024-03-07 | 2
Equipa | High Risk |  | 100% | 2024-03-07 | 2
Plano de Execução | High Risk |  | 100% | 2024-03-07 | 2
Diagrama de Gantt | High Risk |  | 100% | 2024-03-05 | 22
Revisão e Aprovação | High Risk |  | 100% | 2024-03-08 | 2
Levantamento de Requisitos
Definição do Método | High Risk |  | 100% | 2024-03-11 | 4
Levantamento de Requisitos | High Risk |  | 100% | 2024-03-11 | 4
Análise de Requisitos | High Risk |  | 100% | 2024-03-16 | 2
Validação | High Risk |  | 100% | 2024-03-18 | 2
Modelo Conceptual
Definição do Processo de Modulações | High Risk |  | 100% | 2024-03-21 | 3
Criação do Modelo Conceptual | High Risk |  | 100% | 2024-03-23 | 4
Revisão e Validação | High Risk |  | 100% | 2024-03-27 | 4
Implementação Física
Tradução do Modelo Lógico/Interrogações | High Risk |  | 100% | 2024-04-29 | 10
Definição e Caracterização de Vistas | High Risk |  | 100% | 2024-05-10 | 5
Cálculo do Espaço | High Risk |  | 100% | 2024-05-15 | 8
Indexação do Sistemas de Dados | High Risk |  | 100% | 2024-05-22 | 5
Definição do Plano de Segurança | High Risk |  | 100% | 2024-05-27 | 2
Implementação do Sistema de Recolha de Dados
Definição do Sistema | High Risk |  | 100% | 2024-05-24 | 2
Implementação | High Risk |  | 100% | 2024-05-26 | 1
Revisão do Sistema | High Risk |  | 100% | 2024-05-28 | 1

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2024-05-28 |  |  |  |  | junho | [34 empty] | julho
Scrolling increment: | 5 | time axis 2024-06-02 to 2024-07-27
Milestone description | Category | Assigned to | Progress | Start | Days | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-28 | 3
Task 2 | Milestone |  |  | 2024-06-02 | 1 | bar: d
Task 3 | Low Risk |  | 50% | 2024-05-25 | 10
Task 4 | Milestone |  |  | 2024-06-17 | 1 | bar: s
Task 5 | Med Risk |  | 10% | 2024-06-03 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-03 | 13
Task 2 | On Track |  | 50% | 2024-06-05 | 9
Task 3 | Low Risk |  | 33% | 2024-06-10 | 11
Task 4 | Milestone |  |  | 2024-06-12 | 1 | bar: q
Task 5 |  |  |  | 2024-06-13 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-12 | 4
Task 2 | Med Risk |  |  | 2024-06-15 | 14
Task 3 | On Track |  |  | 2024-06-30 | 6
Task 4 | Goal |  |  | 2024-07-04 | 3 | q: 2; s: 2; s: 2
Task 5 | Low Risk |  |  | 2024-06-03 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-07 | 15
Task 2 |  |  |  | 2024-07-21 | 5
Task 3 | Milestone |  |  | 2024-09-01 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2024-05-28 |  |  |  |  | junho | [34 empty] | julho
Scrolling increment: | 5 | time axis 2024-06-02 to 2024-07-27
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-06-02 to 2024-07-27
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-28 | 3
Task 2 | Milestone |  |  | 2024-06-02 | 1 | bar: 2024-06-02
Task 3 | Low Risk |  | 50% | 2024-05-25 | 10
Task 4 | Milestone |  |  | 2024-06-17 | 1 | bar: 2024-06-17
Task 5 | Med Risk |  | 10% | 2024-06-03 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-03 | 13
Task 2 | On Track |  | 50% | 2024-06-05 | 9
Task 3 | Low Risk |  | 33% | 2024-06-10 | 11
Task 4 | Milestone |  |  | 2024-06-12 | 1 | bar: 2024-06-12
Task 5 |  |  |  | 2024-06-13 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-12 | 4
Task 2 | Med Risk |  |  | 2024-06-15 | 14
Task 3 | On Track |  |  | 2024-06-30 | 6
Task 4 | Goal |  |  | 2024-07-04 | 3 | 2024-07-04: 2; 2024-07-05: 2; 2024-07-06: 2
Task 5 | Low Risk |  |  | 2024-06-03 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-07 | 15
Task 2 |  |  |  | 2024-07-21 | 5
Task 3 | Milestone |  |  | 2024-09-01 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one